## Roadmap Status
Implementation Status

## Group 3
Gigya Consent Management Implementation Metrics | Deliverable | ALLTEC (FOBA) | Devicor (Mammotome) | LINX | Trojan Technologies | TBD
Implementation Key Milestones
Planning Status
Workshop Scheduled (Pre-Reqs Completed) |  | Completed | Completed | Completed | 2019-07-24
Current State - Use Cases / Data Flows | D | Completed | 2019-07-15 | 2019-07-18
Team Chart | D | 2019-07-03 | 2019-07-22 | 2019-07-18
Scope Status
Use Case & Data Mapping Review | D | 2019-07-12 | 2019-07-17 | 2019-07-18
Design Status
OpCo Technical Design Doc Finalized | D | 2019-07-12 | 2019-07-25 | 2019-07-23
Playbooks Finalized (Informatica/SFTP/ Marketo - Simplified/ SQL DB) | D | TBD | NA | TBD
Execution Status
POCs completed |  | 2019-07-02 | 2019-07-25 | 2019-07-18
Development/ Unit Testing Completed |  | 2019-07-26 | 2019-08-09 | 2019-08-02
Initial Extract & Load Development Complete |  | 2019-07-26 | 2019-08-09 | 2019-08-02
System Integration Testing Complete (Verification) | D | 2019-08-02 | 2019-08-16 | 2019-08-09
User Acceptance Testing (UAT) Complete (Validation) | D | 2019-08-09 | 2019-08-23 | 2019-08-23
Implementation Status - PROD
End User Training (OpCo Privacy Lead/ Admin) |  | 2019-08-09 | 2019-08-23 | 2019-08-23
User Provisioning |  | 2019-08-12 | 2019-08-27 | 2019-08-27
Initial Data Load/ Verification |  | 2019-08-14 | 2019-08-28 | 2019-08-28
Integration Migration/ Switch-On |  | 2019-08-14 | 2019-08-28 | 2019-08-28
Operational Readiness Verification |  | 2019-08-14 | 2019-08-28 | 2019-08-28
Go-Live |  | 2019-08-15 | 2019-08-29 | 2019-08-29
Clean up data from non-prod instances/ switch-off non-prod interfaces
Number of Integrations |  | 1
Estimated Customer Contacts for Initial Data Load |  | 26000
Estimated Average Total of New Contacts per Month |  | TBD
Current Open Issue Count
Current High Risks
D = Deliverable is required to be uploaded to Danaher - Gigya Exchange site
Blue borders indicate new updates from prior week
Green cells represent completed milestones
Yellow cells represent work in progress
Note on D13: Mali, Asha S: Leveraging IDT Informatica playbook
Note on B19: Asha S Mali: Deliverables = Executed Test Scripts
Note on B20: Asha S Mali: Deliverables = Executed Test Scripts
Note on A36: Asha S Mali: Source = Open Issues documented on Danaher - Gigya Exchange
Note on A37: Asha S Mali: Source = High Risks documented on Danaher - Gigya Exchange

## Group 2
Gigya Consent Management Implementation Metrics | Deliverable | LS - IDT | WQ - Pall Water | PID - Laetus
Implementation Key Milestones
Planning Status
Questionnaire - Review/ Update Data Points | D | NA | NA | NA
Workshop Scheduled (Pre-Reqs Completed) |  | 2019-03-29 | 2019-04-23 | 2019-05-01
Current State - Use Cases / Data Flows | D | 2019-04-02 | 2019-04-23 | 2019-05-01
Team Chart | D | 2019-04-02 | 2019-04-23 | 2019-05-14
Project Schedule/ Action Plan | D | NA | NA | 2019-05-09
Scope Status
POCs identified |  | 2019-04-02 | 2019-04-24 | 2019-05-01
OpCo Project Fit BluePrint Privacy Review |  | 2019-04-24 | 2019-05-17 | 2019-05-22
OpCo Project Fit BluePrint Finalized | D | 2019-04-24 | 2019-05-22 | 2019-05-22
Design Status
OpCo Technical Design Doc Finalized | D | 2019-04-17 | 2019-05-22 | 2019-05-17
Playbooks Finalized (Informatica/SFTP/ Marketo - Simplified/ SQL DB) | D | NA | 2019-06-17 | 2019-06-27
Execution Status
POCs completed |  | 2019-04-04 | 2019-04-25 | 2019-05-03
Integration Development Complete (Code Freeze) |  | 2019-04-24 | 2019-05-31 | 2019-05-29
Migration Development Complete |  | 2019-04-24 | 2019-05-31 | 2019-05-29
System Integration Testing Complete (Verification) | D | 2019-04-24 | 2019-05-31 | 2019-06-12
UAT Complete (Validation) | D | 2019-05-07 | 2019-06-14 | 2019-06-21
Implementation Status - PROD
End User Training (OpCo Privacy Lead/ Admin) |  | 2019-04-24 | 2019-06-19 | 2019-06-14
User Provisioning |  | 2019-05-10 | 2019-06-21 | 2019-06-26
Intial Data Load/ Verification |  | 2019-05-10 | 2019-06-25 | 2019-06-26
Integration Migration/ Switch-On |  | 2019-05-10 | 2019-06-25 | 2019-06-26
Operational Readiness Verification |  | 2019-05-14 | 2019-06-25 | 2019-06-27
Go-Live |  | 2019-05-11 | 2019-06-25 | 2019-07-05
Number of Integrations |  | 1 | 1 | 1
Estimated Customer Contacts for Initial Data Load |  | 2200+ | 3164 | 2300
Estimated Average Total of New Contacts per Month |  | 300 | TBD | 30
Current Open Issue Count
Current High Risks
D = Deliverable is required to be uploaded to Danaher - Gigya Exchange site
Blue borders indicate new updates from prior week
Green cells represent completed milestones
Yellow cells represent work in progress
Note on E21: Mali, Asha S: 6/4: Laetus development to complete by 6/7 6/4: Country Code was added to SmartCRM. Data is updated manually.
Note on B23: Asha S Mali: Deliverables = Executed Test Scripts
Note on C23: Asha S Mali: Deliverable NA to IDT
Note on B24: Asha S Mali: Deliverables = Executed Test Scripts
Note on E33: Mali, Asha S: Total EU - 7714 Total RU - 32
Note on C36: Mali, Asha S: Global Contacts - 20K
Note on C37: Mali, Asha S: For Global
Note on A38: Asha S Mali: Source = Open Issues documented on Danaher - Gigya Exchange
Note on A39: Asha S Mali: Source = High Risks documented on Danaher - Gigya Exchange

## Group 1
Gigya Consent Management Implementation Metrics | Deliverable | Beckman | Kavo Kerr | Videojet | Hach | SCIEX
Implementation Key Milestones
Planning Status
Questionnaire | D | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
Workshop Scheduled |  | Complete | Complete | Complete | Complete | Complete
Current State - Use Cases / Data Flows | D | 2018-03-21 | 2018-05-28 | 2018-06-12 | 2018-04-16 | 2018-08-10
Team Chart | D | 2018-03-21 | 2018-05-28 | 2018-06-13 | 2018-04-17 | 2018-08-13
Project Schedule | D | 2018-08-28 | 2018-09-08 | 2018-09-07 | 2018-10-25 | 2018-08-31
Scope Status
POCs identified |  | 2018-03-30 | 2018-06-07 | 2018-06-19 | 2018-07-19 | 2018-08-31
OpCo Project Fit BluePrint Finalized | D | 2018-07-27 | 2018-08-17 | 2018-06-29 | 2018-08-10 | 2018-09-07
Design Status
OpCo Technical Design Doc Finalized | D | 2018-08-03 | 2018-09-07 | 2018-10-24 | 2018-08-10 | 2018-09-07
Playbooks Finalized | D | 2018-08-03 | 2018-09-14 | 2018-10-24 |  | 2018-09-07
Execution Status
POCs completed |  | 2018-05-18 | 2018-08-01 | 2018-10-02 | 2018-10-25 | 2018-09-07
Integration Development Complete (Code Freeze) |  | 2018-10-18 | 2018-11-02 | 2018-10-26 | 2018-10-24 | 2018-10-12
Migration Development Complete |  | 2018-10-18 | 2018-11-02 | 2018-10-26 | 2018-11-01 | 2018-10-12
System Integration Testing Complete (Verification) | D | 2018-10-22 | 2018-11-16 | 2018-10-26 | 2019-05-31 | 2018-10-12
UAT Complete (Validation) | D | 2018-11-05 | 2018-11-30 | 2018-10-26 | 2019-07-19 | 2018-10-12
Go-Live |  | 2018-11-09 | 2019-09-30 | 2019-05-31 | TBD | 2018-10-12
Number of Integrations |  | 5 | 5 | 3 | 3 | 1
Current Open Issue Count | 6
Current High Risks | 0
D = Deliverable is required to be uploaded to Danaher - Gigya Exchange site
Blue borders indicate new updates from prior week
Green cells represent completed milestones
Note on G5: Meinhardt, Eileen M: Scheduled for 8/21 - 8/23
Note on C8: Meinhardt, Eileen M: Chg'd from 8/10 to 8/24/18 Chg'd from 7/27/18 to 8/10/18
Note on F8: Meinhardt, Eileen M: 10/25: per email from Wendy Revised date rec'd from Wendy 9/19. Wendy provided 8/31 target date on 8/23. Hach Lead on PTO 7/9 week, and business travel 7/16 week. Plans to resume project 7/23 week.
Note on D12: Meinhardt, Eileen M: 8/7/18: PM provided this target date today. Per Kavo PM 6-29-18: The PFB is not finalized as the integration with two of our third party applications need an technical review with those vendors first
Note on F12: Meinhardt, Eileen M: 7/25: Hach is targeting to finalize 8/10 Gigya provided draft at the end of workshop. Hach to provide comments/updates to Gigya.
Note on C15: Meinhardt, Eileen M: 8/2 - Chg'd from 7/27/18 to 8/3/18. TDD has been agreed upon by Beckman team. Last edits submitted to Gigya.
Note on D15: Meinhardt, Eileen M: 8/7/18: EM to ask Gigya when they can provide 1st complete draft, then 1 week from that date will be the target date for finalizing the TDD
Note on D19: Meinhardt, Eileen M: Per Kavo PM 8-07-18: plan to only do 1 POC, KavoShop. It was completed earlier, but just now reporting it as completed.
Note on E19: Meinhardt, Eileen M: Date provided by Donald via email 8/2
Note on F19: Meinhardt, Eileen M: 10/25: rec'd this update from Wendy Revised date rec'd from Wendy 9/19. Date provided by Wendy during 8/2 Pgm mtg.
Note on C20: Meinhardt, Eileen M: 9/28: chg'd from 9/28 to 10/08 due to gigya issue 8/9: At risk: Sitecore external resources have limited availability in Aug. 10/11: chg'd from 10/8 to 10/15 due to Gigya delays regarding dataflow setups for Eloqua/Pardot.
Note on F20: Meinhardt, Eileen M: Per email from Wendy
Note on C21: Meinhardt, Eileen M: 9/28: chg'd from 9/28 to 10/08 due to gigya issue 8/9: At risk: Sitecore external resources have limited availability in Aug. 10/11: chg'd from 10/8 to 10/15 due to Gigya delays regarding dataflow setups for Eloqua/Pardot.
Note on A22: Meinhardt, Eileen M Deliverables = Executed Test Scripts
Note on C22: Meinhardt, Eileen M: 10/11: chg'd from 10/12 to 10/22 due to delays w/Gigya completing dataflows for Eloqua/Pardot
Note on F22: Mali, Asha S: Hach configuration for US - after SIT completes/ configuration will have to switched off for US and enable it for EU
Note on A23: Meinhardt, Eileen M: Deliverables = Executed Test Scripts
Note on G24: Monk, Rebecca: Golive call 10/12/2018, all data following to Gigya, Gigya to send final files over to SCIEX and SCIEX to confirm all data looks correct, once we confirm, we are officially live
Note on A27: Meinhardt, Eileen M: Source = Open Issues documented on Danaher - Gigya Exchange stie
Note on A28: Meinhardt, Eileen M: Source = High Risks documented on Danaher - Gigya Exchange site